## Goods
Procurement Schedule for Goods under SSA for the year 2015-16
Uttarakhand | [14 empty] | Rs -lakh
S. No. | Description of works | Quantity in numbers | Method of Procurement | Estimated cost (Rs in lakhs) | Procurement Action 2015-16
[5 empty] | April | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Text books | PS 351670 | Open Tender- State Govt.- Edu. Deptt. | 1132.81 | Procurement Action 2015-16 April: 6
UPS 242120
| Total | 593790
2 | School Equipment under School Grant | PS 12718 | Without tender as Per State Govt. rules for small value purchases | 635.9 | Procurement Action 2015-16 Aug.: 1; Procurement Action 2015-16 Sep.: 5; Procurement Action 2015-16 Oct.: 6
|  | UPS 5367 |  | 375.69 | Procurement Action 2015-16 Aug.: 1; Procurement Action 2015-16 Sep.: 5; Procurement Action 2015-16 Oct.: 6
| Total | 18085 |  | 1011.59
3 | Provision of 2 sets of Uniform | 694488 | Without Tender as per Procurement Rules of SMC/ward Committee | 2777.95 | Procurement Action 2015-16 June: 1; Procurement Action 2015-16 Aug.: 5-6
4 | Computer Aided Education (CALP) | 288 school | Open Tender- State Govt.- Edu. Deptt./DGSD | 537.8 | Procurement Action 2015-16 July: 1; Procurement Action 2015-16 Oct.: 2; Procurement Action 2015-16 Nov.: 3-4; Procurement Action 2015-16 Dec.: 5; Procurement Action 2015-16 Jan.: 6
5 | IED - Provision of Aids & Appliances | 10596 child | Single Tender through ALIMCO | 317.88 | Procurement Action 2015-16 Sep.: 1; Procurement Action 2015-16 Oct.: 2; Procurement Action 2015-16 Dec.: 5-6
6 | Replacement of Beding for KGBV | 13 school Administration |  | 0.375 | Procurement Action 2015-16 Aug.: 1; Procurement Action 2015-16 Sep.: 2; Procurement Action 2015-16 Oct.: 3-4; Procurement Action 2015-16 Nov.: 5-6
| Method of Procurement |  |  |  | Procurement Action 2015-16 June: Procurement Actions
| Without Tender |  |  |  | Procurement Action 2015-16 June: 1. Preparation of specifications and bids document.
| Single tender |  |  |  | Procurement Action 2015-16 June: 2. Issue of Invitation to bid.
| Open Tender |  |  |  | Procurement Action 2015-16 June: 3. Open bids
| Limited Tender |  |  |  | Procurement Action 2015-16 June: 4. Evaluation
| Rate Contract |  |  |  | Procurement Action 2015-16 June: 5. Award Contracts
| E.Procurement |  |  |  | Procurement Action 2015-16 June: 6. Delivery

## Civil works
Procurement Schedule for Civil Works under SSA for the year 2015-16
Uttarakhand
S. No. | Description of works | Quantity in numbers | Method of Procurement | Estimated cost (Rs in lakhs) | Procurement Action 2015-16
[5 empty] | April | May | June | July | Aug. | Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | New Primary School |  | Community construction | 151.605 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Sep.: 6; Procurement Action 2015-16 Nov.: 7; Procurement Action 2015-16 Jan.: 8; Procurement Action 2015-16 March: 9
3 | Reconstruction of completely damaged schools in natural calamity |  | Community construction | 65.68 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Sep.: 6; Procurement Action 2015-16 Nov.: 7; Procurement Action 2015-16 Jan.: 8; Procurement Action 2015-16 March: 9
4 | Dilapidated Building |  | Community construction | 170.77 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Sep.: 6; Procurement Action 2015-16 Nov.: 7; Procurement Action 2015-16 Jan.: 8; Procurement Action 2015-16 March: 9
5 | Additional Class Room | 122 | Community construction | 1372.34 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Aug.: 6; Procurement Action 2015-16 Oct.: 7; Procurement Action 2015-16 Dec.: 8; Procurement Action 2015-16 Jan.: 9
6 | Toilet/Urinals Plain | 34 | Community construction | 59.84 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Aug.: 6; Procurement Action 2015-16 Sep.: 7; Procurement Action 2015-16 Oct.: 8; Procurement Action 2015-16 Nov.: 9
7 | Separate Girls Toilet Hill | 73 | Community construction | 213.52 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Aug.: 6; Procurement Action 2015-16 Sep.: 7; Procurement Action 2015-16 Oct.: 8; Procurement Action 2015-16 Nov.: 9
8 | Boundary Wall |  | Community construction | 1262.9933 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Aug.: 6-7; Procurement Action 2015-16 Sep.: 8-9
9 | Office-cum-store-cum-Head Teacher's room (Primary) |  | Community construction | 71.4 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Aug.: 6; Procurement Action 2015-16 Oct.: 7; Procurement Action 2015-16 Dec.: 8; Procurement Action 2015-16 Jan.: 9
10 | Residential Schools/hostels for specific category of children (c) Refurbishing unused old buildings |  | Community construction | 10.5 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Aug.: 6; Procurement Action 2015-16 Oct.: 7; Procurement Action 2015-16 Dec.: 8; Procurement Action 2015-16 Jan.: 9
11 | Major Repairs to partially damaged to schools | 67 | Community construction | 249.46 | Procurement Action 2015-16 July: 5; Procurement Action 2015-16 Sep.: 6; Procurement Action 2015-16 Oct.: 7; Procurement Action 2015-16 Nov.: 8; Procurement Action 2015-16 Dec.: 8
| Grand Total |  |  | 3628.1083
| Method of Procurement |  |  |  | Procurement Action 2015-16 June: Procurement Actions
| Community Construction |  |  |  | Procurement Action 2015-16 June: 1. Preparation of specifications and bids document.
| Open Tender |  |  |  | Procurement Action 2015-16 June: 2. Issue of Invitation to bid.
| Open Tender |  |  |  | Procurement Action 2015-16 June: 3. Open bids
| Limited Tender |  |  |  | Procurement Action 2015-16 June: 4. Evaluation of bids
| Rate Contract |  |  |  | Procurement Action 2015-16 June: 5. Award of contracts
| E.Procurement |  |  |  | Procurement Action 2015-16 June: 6. Construction 25% complete.
7. Construction 50% complete.
8. Construction 75% complete.
9. Construction 100% complete.

## Consultancy
List of Consultancy Services to be Hired under SSA for the year 2015-16
Uttarakhand
S. No. | Name of Consultancy | estimated man months for each consultancy | No. of consultancy | Total estimated cost (Rs. In Lakhs) | Quarterwise Procurment 2013-14 | [7 empty] | Remarks on proposed method of procurment
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | No. | Cost. | No. | Cost. | No. | Cost. | No. | Cost.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | CA firm for external audit | 3 month | 2 | 10 |  |  |  |  | 3 | 10 |  |  | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India or as per GOI instructions.
2 | Research Study | 12 month | 2 | 154.48 |  | 0 |  | 42 |  | 60 |  | 52.48 | Short listing as per expertise & objective criteria laid down in financial / procurement manual of Govt. of India or as per GOI instructions.